## Sheet1
BIT 4454 Agile Product Backlog
| My VT Email | kashvi@vt.edu | Our client organization: | Virginia Tech – Pamplin College of Business
| My Full Name | Kashvi Patel | Team members (and roles): | Kashvi Patel (Project Manager ); Ben Schwab (Requirements Analyst); Thomas McHugh (Data Manager); Anthony Bible (Process Designer); Alexa Corales (UX Lead); Kenny Le (BI Analyst); Giovanni Marroquin (BI Analyst); Hannah Nguyen (Developer)
| Our Team Name | SMU Peer Evaluation System | Project objective: | Design and implement a peer evaluation system that allows students to submit structured feedback, instructors to manage evaluation timing, and administrators to analyze results, while supporting team accountability and scalable data-driven insights.
| Today's Date: | 2026-01-14 14:50
ID | Theme | As a … | … I want to … | … so that … | Notes | Estimate (hrs) | Deadline | Priority | Date at "Done" | Status
1 | Peer Evaluation Core | Student | submit a peer evaluation form | my contributions and my teammates’ contributions can be assessed fairly. | Core MVP functionality for Sprint 1. Enables collection of peer feedback tied to specific team members and learning outcomes. | 8 | 2026-01-16 | High | 2026-01-13 | Done!
2 | Peer Evaluation Core | Student | select teammates to evaluate | I can provide required feedback for each team member. | Supports correct mapping of evaluators to evaluatees. Required dependency for peer evaluation submission in Sprint 1. | 6 | 2026-01-16 | High | 2026-01-14 | Done!
3 | Peer Evaluation Core | Instructor | view peer evaluation results | I can review individual and team performance | Provides visibility into submitted evaluations. Supports instructional review and downstream reporting. | 6 | 2026-01-16 | High | 2026-01-15 | Done!
4 | Evaluation Analytics | Administrator | view the total number of peer evaluations submitted by course and date | participation, trends, and outcomes can be analyzed. | Bar or line chart showing submission volume over time. Validates system usage and data completeness. | 4 | N/A | Medium |  | Backlogged
5 | Evaluation Analytics | Administrator | view average peer evaluation scores by evaluation criterion | strengths and weaknesses across teams can be identified | Aggregated averages per learning outcome or evaluation question. Supports quality assessment. | 5 | N/A | Medium |  | Backlogged
6 | Evaluation Analytics | Administrator | view peer evaluation completion rates per course | low participation courses can be flagged | Percentage-based chart comparing submitted evaluations vs expected evaluations. | 4 | N/A | Medium |  | Backlogged
7 | System Administration | Administrator | manage courses and student enrollment | peer evaluations are assigned correctly | Administrative setup functionality. | 6 | N/A | Low |  | Backlogged
8 | Reporting | Administrator | export peer evaluation results | results can be archived or shared | CSV/PDF export of evaluation data. Deferred until after core analytics. | 4 | N/A | Low |  | Backlogged
Backlogged
Backlogged
Backlogged
Backlogged